## Risk register
Risk | Area | Evidence basis | Initial risk view | Business impact | Recommended action | Anonymous Company response / mitigation context
Potential SQL injection, legacy salted SHA256 password hashing not aligned with modern best practice, hardcoded keys, and no evident anti-CSRF in DanceWorks Online Web App | Security | Confirmed from repository/code evidence | High | Backend compromise, data exposure, operational disruption | Treat as day-one containment; validate production exploitability, restrict exposure, remediate highest-risk paths | Known internally. Salted SHA256 hashing acknowledged as legacy. ViewState validation cited as anti-CSRF coverage for WebForms. Anonymous Company agrees live hardcoded values should be validated and any live secrets rotated day one. SQL injection reachability should be validated in production context.
Plaintext credentials / weak secret segregation in legacy config (web.config) and other secret-hygiene issues | Secrets / repo hygiene | Confirmed from repository/code evidence | High | Credential leakage, unauthorized access, broader infrastructure exposure | Rotate sensitive values, externalize secrets, confirm live usage, restrict access | Known internally. web.config values are plaintext on the VM-hosted WebForms app and present in source control. Exposure bounded by IP-restricted VM access and MFA-protected source control. Rotation and externalization to Azure Key Vault / App Service settings accepted as highest-value near-term action.
Migration-operability fragility in payments, webhook processing, background workers, scheduling, messaging, and reporting | Scalability / operability | Confirmed from repository/code evidence | High | Service degradation during coexistence, manual ops burden, delayed processing | Increase monitoring, identify failure thresholds, prioritize contingency plans around these workflows | Known operationally. Background workers, scheduling, and webhook processing reported stable in production but lightly documented. Azure monitoring and alerting already in place. Anonymous Company agrees increased monitoring and documented failure thresholds are appropriate migration-period actions.
Legacy technology and supportability concentration in DanceWorks Online Web App (ASP.NET Web Forms, VB.NET, .NET Framework 4.8, legacy stack patterns) | Technology lifecycle | Confirmed from repository/code evidence; final severity pending infrastructure versions | High | Harder patching/support, reduced resilience, harder incident response | Confirm production versions, assess support status, minimize change surface during migration | Known and expected. Production stack currently supported (.NET Framework 4.8, IIS 10, Windows Server 2022, Azure SQL Database). Risk is ongoing supportability and legacy architecture, not immediate end-of-support. Crystal Reports remains required in production.
Contributor concentration / bus-factor risk in anonymous-company-customer, anonymous-company-shared, app-components, and to a lesser extent anonymous-company-studio | Code history / continuity | Confirmed from repository/code evidence | Medium-High | Support fragility, slower troubleshooting, dependency on individuals | Identify independent support owners, document critical workflows, cross-train where possible | Known. DJ Roedger and Mark Hummel can independently support the core platform; Leland Reardon has full Flutter knowledge. TSA retains DJ for 12 months and Anonymous Company expects Mark continuity post-close. Main gap is documentation rather than absence of support personnel.
Runtime-reachable dio dependency risk in anonymous-company-studio | Dependencies | Confirmed from repository/code evidence | Medium-High | Narrow runtime dependency exposure in studio-facing app | Patch/upgrade during normal maintenance window; monitor advisories | No direct Anonymous Company response yet. Remains open as a normal maintenance / patching item unless Anonymous Company provides further dependency-management context.
Shared-library coupling across anonymous-company-shared and app-components affecting multiple migration-facing apps | Technical debt / dependencies | Confirmed from repository/code evidence | Medium | Cross-application regression risk during migration changes | Minimize shared-layer changes, document dependency points, test cross-app impact carefully | Anonymous Company agrees changes to anonymous-company-shared and app-components should be minimized during migration to reduce cross-application regression risk.
Manual fork of flutter_stripe in anonymous-company-customer | OSS / dependencies | Confirmed from repository/code evidence | Medium | Maintenance drag, upstream drift, patch lag | Confirm necessity, review fork delta, plan maintenance ownership | The fork was created to address an Android performance bug in the upstream package. Anonymous Company reported the issue and submitted a PR, which was merged in February 2026. The fork is no longer believed to be strategically necessary, but replacement requires rigorous payment testing because payments are a primary feature.
Minor GPL footprint in anonymous-company-studio and vendored/proprietary dependency mix in DanceWorksOnline | OSS / licensing | Inferred from code, pending management confirmation | Low-Medium | Potential notice/compliance follow-up | Confirm what is distributed and whether notices/commercial terms are already managed | Anonymous Company confirms no private package feeds or proprietary binary dependencies are required to build or run the platform. All service accounts are company-owned. Distribution / notice specifics still require confirmation where relevant.
Build-time-only dependency findings in anonymous-company-customer and other non-runtime noise | Dependencies | Confirmed from repository/code evidence | Low | Limited direct runtime effect | Track separately; do not over-prioritize in migration risk register | Now further de-risked by Anonymous Company's confirmation that Node, Python, and Ruby are confined to test, build, or distribution tooling and do not materially affect production runtime risk.

## Version history
Version | Date | Notes
1.0.0 | 16th April 2026 | Initial version based on code review
1.0.1 | 17th April 2026 | Slightly updated password hashing wording and priority of "public reachable admin area" based on additional Anonymous Company context provided
1.0.2 | 21st April 2026 | Additional context provided by Anonymous Company Software for technology lifecycle, dependencies and third-party services, code history / contributor continuity, and preliminary risk-register prioritization.
1.0.3 | 22nd April 2026 | Updated Anonymous Company comment entries across the preliminary risk register to reflect final management responses. Clarified compensating controls, day-one containment priorities, production supportability context, contributor continuity mitigation, and the now-understood flutter_stripe replacement path. Confirmed that Node, Python, and Ruby are limited to test/build/distribution tooling and do not materially affect production runtime risk. No structural changes made to the register itself beyond comment refinement.